August 20, 2003

# Plan for responding to the legal challenge to the student assignment process

- Reaffirm the commitment of Berkeley Unified School District to equal educational opportunity and our belief that educational diversity is a highly valued component of successful educational outcomes for all of our students. The commitment to this important and precious legacy is a primary value in our community.

Lead:

Michele

Outside resources:

Sheila

Tasks:

Explain alternative assignment procedures in a straightforward way

Schedule Board meetings

Prepare materials for Board

Distribute Student Assignment Committee Statement of Beliefs?

Draft alternative to Resolution 7008? (Sheila will assist )

Assemble small task force?

Timeline:

By September 17, positive Board vote: BUSD and the Board of Education reaffirm the value of educational diversity and its commitment to equal educational opportunity for all students.

- Work with legal counsel to quickly respond to the complaint with efforts to dismiss and/or stay the litigation.

Lead:

Francisco

Outside resources:

District legal counsel

Pro bono legal counsel?

Tasks:

Provide factual information regarding allegations in complaint

Provide other documentation as needed

Meet with lawyers to discuss strategy

Reporting:

Meet with Michele as needed

Timeline:

As soon as possible after District is served

- Assess and adjust as needed our plans developed last year for a student assignment plan that does not use race as a factor but that maintains racial diversity in all of our schools.

Lead:

Bruce

Tasks:

Review work from last year

Modify as necessary

Run again

Compare outcomes under mock runs to current outcomes

Meet with Francisco daily as needed

Reporting:

Bruce reports to Michele daily by phone or meeting

Timeline:

One week